## Sheet1
| TIME | DESCRIPTION | RESOURCE/NAME
WEEK 1
2015-07-07 | 5:30 - 7:30 | Developing/designing of Web App | Nicholas Hoskins, Angelika Wilson, Grace Markham, John Gil
2015-07-08 | 5:30 - 7:30 | Validating report outline, resources, requirements | Project group (Interns)
2015-07-09 | 5:30-7:30 | Developing/Work on tasks | Project group (Interns)
WEEK 2
2015-07-14 | 5:30 - 7:30 | Developing/ Work on Tasks | Project group (Interns)
2015-07-15 | 5:30 - 7:30 | Working on report & presentation | Project group (Interns), Coral Wells, Ciera Fox, Sandra DeSilva
2015-07-16 | 5:30-7:30 | Developing/designing of Web App | Nicholas Hoskins, Angelika Wilson, Grace Markham
WEEK 3
2015-07-21 | 5:30 - 7:30 | Layout/design of report and powerpoint | Project group (Interns), Ciera Fox, Derwin Adams
2015-07-20 | 5:30-7:30 | Work on tasks | Project group (Interns)
2015-07-23 | 5:30 - 7:30 | Work on report | Project group (Interns), Ciera Fox, Derwin Adams
WEEK 4 - Cup Match Week
2015-07-28 | 5:30 - 7:30 | Finalization of report and powerpoint presentation/ Allocate presentation parts | Project group (Interns), Ciera Fox, Derwin Adams
2015-07-29 | 5:30 - 7:30 | Finalizing web app/testing | Project group (Interns), Nocholas Hoskins, Angelika Wilson, John Gil
WEEK 5
2015-08-04 | 5:30 - 7:30 | Presentation practice/tips, User Test Web Application | Project group (Interns), Marisa Stones, Sheldon Jones
2015-08-05 | 5:30-7:30 | Final Report Draft, Final Presentation, User Test App, Make Amendments | Project group (Inters), Any one willing to help (Audience willing members, alumni etc.)
2015-08-06 | 5:30 - 7:30 | Finalization of presentation/practice | Project group (Inters), Any one willing to help (Audience willing members, alumni etc.)
WEEK 6 - Presentation, Friday, August 14, 2015
8/9/15-8/13/15 | 5:30-Until | Presentation Practice | Project group (Interns) , Anyone willing to help (Audience members, alumni etc)
2015-08-14 | Arranged Time | Presentation, App Demonstration | Project group (Interns) , Anyone willing to watch (Audience members, alumni, board members, stakeholders)